## Sheet1
Terre Bonne Culvert Replacement & Pavement Restoration
Pay Item Sheet
2012-01-30
ITEM DESCRIPTION | UNIT | QNTY | UNIT PRICE | TOTAL
Mobilization | 1 | LS | 0 | 0
MOT | 1 | LS | 0 | 0
Silt Fence | 210 | LF | 0 | 0
Tree Protection | 100 | LF | 0 | 0
Tree Mitigation | 1 | LS | 0 | 0
Clearing and Grubbing | 0.18 | AC | 0 | 0
Demo Asphalt | 545 | SY | 0 | 0
Demo Flume | 1 | EA | 0 | 0
Relocated Sprinkler | 1 | EA | 0 | 0
Relocate Mailbox | 1 | EA | 0 | 0
Remove Headwall | 1 | LS | 0 | 0
Cut | 160 | CY | 0 | 0
Fill | 60 | CY | 0 | 0
Overexcavate and Backfill | 20 | SY | 0 | 0
Concrete Endwalls | 2 | EA | 0 | 0
Box Culvert | 25 | LF | 0 | 0
Temporary Asphalt Millings | 1 | LS | 0 | 0
Approved Temporary Roadway Stabilization | 1 | LS | 0 | 0
1.5" Asphalt | 445 | SY | 0 | 0
1" Asphalt Overlay | 4725 | SY | 0 | 0
6" Base | 445 | SY | 0 | 0
1' Subgrade | 465 | SY | 0 | 0
Cellular Confinement System | 45 | SY | 0 | 0
Geotextile | 60 | SY | 0 | 0
RipRap | 6 | TN | 0 | 0
4" Stone | 12 | TN | 0 | 0
Turf Reinforcement Mat | 60 | SF | 0 | 0
Seed and Mulch | 3500 | SF | 0 | 0
Shrubs | 1 | LS | 0 | 0
Concrete Collar | 1 | EA | 0 | 0
Modify Manhole | 1 | LS | 0 | 0
As-Builts and Layout | 1 | LS | 0 | 0
Handrail | 50 | LF | 0 | 0
TOTAL |  |  |  | 0